## Timeline
Gantt Chart
Project : Cartrity (Aplikasi Online Shop dengan Donasi)
Kelompok 1
Task Name | Start | End | Duration (days)
Exploring Tools | 2018-02-27 | 2018-03-31 | 32
Collecting Data | 2018-02-27 | 2018-03-31 | 32
Training Tools | 2018-02-28 | 2018-03-07 | 7
Data Normalization | 2018-03-13 | 2018-03-31 | 18
Menyiapkan Database | 2018-03-13 | 2018-03-20 | 7
Inserting Data | 2018-03-13 | 2018-03-31 | 18
Creating Front End | 2018-03-07 | 2018-03-21 | 14
Creating Back End | 2018-03-07 | 2018-03-21 | 14
Synchronizing Application | 2018-03-21 | 2018-03-28 | 7
Finalizing | 2018-03-28 | 2018-03-30 | 2
Finalizing | 2018-03-30 | 2018-04-02 | 3
Finalizing | 2018-04-03 | 2018-04-05 | 2
`

## Project Tracking
Project Tracking
Project : Cartrity (Aplikasi Online Shop dengan Donasi)
Kelompok 1
| Projects |  |  |  |  | Deliverable(s) |  | Hours
Status | Priority | Deadline | Task | Assignee | Description | Deliverable | % Done | Est. Hrs | Actual Hrs
Cartrity
x | Low | 2018-03-06 | Exploring Web Scrapper | Hamzah | Exploring tools for Web Scrapping that can be used for Collecting Data |  | 0%
x | Low | 2018-03-06 | Exploring Web Scrapper | Afif Rana | Exploring tools for Web Scrapping that can be used for Collecting Data |  | 0%
x | Low | 2018-03-06 | Exploring Java for Web | Gibran | Exploring tools for Developing Website using Java |  | 0%
x | Low | 2018-03-06 | Exploring Java for Web | Annazar | Exploring tools for Developing Website using Java |  | 0%

## Issue Tracking
Issue Tracking
Project : Cartrity (Aplikasi Online Shop dengan Donasi)
Kelompok 1
Issue No | Status | Issue Description | Category | Priority | Assignee | Raised By | Open | Close | Comments
1 | Active | Hasil scraping berantakan |  | Medium | Annazar | Annazar | 2018-02-27
2
3
4
5
6
7
8
9
10